## Sheet1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Joseph Marube | Team Lead | j.marube@alustudent.com
Philip Mbogho | Developer | p.mganga@alustudent.com
Davine Uwase | Developer | d.uwase7@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Design ERD in Draw.io | Davine Uwase | 2026-05-15 | Completed | Yes | Task completed as assigned.
| Write DDL: CREATE TABLE + all constraints | Davine Uwase | 2026-05-15 | Completed | Yes | Task completed as assigned.
| Add indexes for performance | Davine Uwase | 2026-05-15 | Completed | Yes | Task completed as assigned.
| Write INSERT statements | Joseph Marube | 2026-05-16 | Completed | Yes | Task completed as assigned.
| Run full schema locally, verify error-free | Joseph Marube | 2026-05-16 | Completed | Yes | Task completed as assigned.
| Run CRUD operations and screenshot and Add constraint violation tests | Joseph Marube | 2026-05-16 | Completed | Yes | Task completed as assigned.
| Create JSON schemas for all 5 entities | Philip Mbogho | 2026-05-17 | Completed | Yes | Task completed as assigned.
| Write complex nested transaction object | Philip Mbogho | 2026-05-17 | Completed | Yes | Task completed as assigned.
| Document SQL to JSON mapping | Philip Mbogho | 2026-05-17 | Completed | Yes | Task completed as assigned.
| Design overall API structure & auth flow | Joseph Marube | 2026-05-28 | Completed | Yes | Task completed as assigned.
| Implement Basic Auth middleware (check_auth, send_401) | Joseph Marube | 2026-05-28 | Completed | Yes | Task completed as assigned.
| Implement all 5 CRUD endpoints (http.server) | Joseph Marube | 2026-05-28 | Completed | Yes | Task completed as assigned.
| Parse modified_sms_v2.xml | Philip Mbogho | 2026-05-28 | Completed | Yes | Task completed as assigned.
| Implement linear search O(n) + dict lookup O(1) | Davine Uwase | 2026-05-29 | Completed | Yes | Task completed as assigned.
| Measure & compare search efficiency (20+ records) | Davine Uwase | 2026-05-29 | Completed | Yes | Task completed as assigned.
| Write docs/api_docs.md - all 5 endpoints | Davine Uwase | 2026-05-29 | Completed | Yes | Task completed as assigned.
| Run curl/Postman tests + save screenshots | Philip Mbogho | 2026-05-29 | Completed | Yes | Task completed as assigned.
| Update README.md | Joseph Marube | 2026-05-30 | Completed | Yes | Task completed as assigned.
| Update AI_usage_log.md | Philip Mbogho | 2026-05-30 | Completed | Yes | Task completed as assigned.
| Update Scrum board | Davine Uwase | 2026-05-30 | Completed | Yes | Task completed as assigned.
| Write PDF report - Sections 02 + 03 | Joseph Marube | 2026-05-30 | Completed | Yes | Task completed as assigned.
| Write PDF report - Sections 04 + 05 | Davine Uwase | 2026-05-30 | Completed | Yes | Task completed as assigned.
| Embed screenshots - Section 06 | Philip Mbogho | 2026-05-30 | Completed | Yes | Task completed as assigned.
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-05-14 | Team Breifing | Joseph Marube | Philip Mbogho Davine Uwase | - Reviewed Week 2 assignment requirements and rubric breakdown - Identified 4 deliverables: ERD, SQL schema, JSON modeling, documentation - Allocated roles - Discussed AI usage policy and what is permitted vs prohibited | - Davine to start ERD design in Draw.io - Next meeting 16 May to check progress
2026-05-16 | Progress followup | Joseph Marube | Philip Mbogho Davine Uwase | - ERD draft and DDL & DML schema were reviewed - Reviewed constraint logic: CHECK on amount, phone, status, role | - Next meeting on 17th to review work done - Review work done offer suggestions on improvements
2026-05-17 | Tasks Review | Joseph Marube | Philip Mbogho Davine Uwase | - Reviewed work done and allocate documentation tasks - Reviewed CRUD operation screenshots and constraint violation tests | - Finish up on AI usage logs, Database Design Document - Update Readme.md and scrum board - Submit assignment
2026-05-23 | Task Allocation | Joseph Marube | Philip Mbogho Davine Uwase | - Reviewed Week 3 assignment - Allocated tasks | - Joseph to start api.py - Philip to start parse_xml.py
2026-05-28 | Code review | Joseph Marube | Philip Mbogho Davine Uwase | - Reviewed api.py - all CRUD endpoints working - Verified parse_xml.py loads 1,610 transactions correctly - Tested Basic Auth with valid/invalid credentials (401 working) - Confirmed dictionary index (TX_INDEX) for O(1) lookup | - Complete API documentation in docs/api_docs.md - Run curl tests and save screenshots - Update AI_Usage_Log.md and Scrum board
2026-05-30 | Final review | Joseph Marube | Philip Mbogho Davine Uwase | - Verified all CRUD endpoints functional - Confirmed screenshots saved in /screenshots folder - Reviewed PDF report sections: - Sections 02-03 (API Security) - Joseph completed - Sections 04-05 (Endpoints + DSA) - Davine completed - Section 06 (Screenshots) - Philip completed - Confirmed GitHub repository has all files | - Joseph to write PDF Sections 02 + 03 - Davine to write PDF Sections 04 + 05 - Philip to embed screenshots for Section 06 - Submit by 30 May 23:59